IT5106 - Software Development Project

Progress Report - 1

Academic Year - 2025

Project Identification Information

| Project title | : Wedding and Event Management System for Chance Palace Hotel Group |
| --- | --- |
| Student’s name with initials | : W. A. A. D. Wijesingha |
| Index no. | : 2014173 |
| Supervisor’s name | : Ranula Gihara Gamage |

| Progress Report Period |  |
| --- | --- |
| Start Date: 24th November 2025 | End Date: 5th January 2026 |
| Work Carried out between this meeting and previous meeting |  |
| • Conducted initial client meeting with Chance Palace Hotel Group management to understand current operational challenges |  |
| • Documented existing manual processes including email correspondence, Excel-based booking tracking, and WhatsApp communication workflows |  |
| • Interviewed key stakeholders: General Manager, Event Manager, and Sales Staff |  |
| • Analyzed existing quotation templates, contract documents, and pricing structures |  |
| • Compiled detailed specifications for all five venues: Grand Ballroom, Garden Terrace, Rooftop Pavilion, Conference Hall, and Poolside Area |  |
| • Documented package details for Silver, Gold, Platinum, and Custom packages |  |
| • Identified integration requirements for email (SMTP) and SMS gateway services |  |
| • Created comprehensive Software Requirements Specification (SRS) document |  |
| • Completed technical feasibility assessment confirming Laravel 11, PHP 8.2+, and MySQL 8.0 as appropriate technologies |  |
| • Conducted economic feasibility analysis demonstrating projected ROI through reduced administrative overhead |  |
| • Performed risk assessment and documented mitigation strategies |  |
| • Compiled complete feasibility study report |  |
| • Designed high-level system architecture following layered architecture pattern |  |
| • Created detailed architecture documentation including component diagrams |  |
| • Designed UI wireframes for public-facing website (home, venues, packages, inquiry pages) |  |
| • Designed UI wireframes for admin dashboard (booking management, calendar, reports) |  |
| • Designed UI wireframes for client portal (booking tracking, payment history, documents) |  |
| • Created high-fidelity UI mockups using Figma |  |
| • Conducted client review session and incorporated feedback |  |
| • Designed comprehensive Entity-Relationship Diagram (ERD) covering 25+ entities |  |
| • Normalized database schema to Third Normal Form (3NF) |  |
| • Created detailed table structures with appropriate constraints, indexes, and foreign key relationships |  |
| • Set up local development environment using Laragon with PHP 8.2 and MySQL 8.0 |  |
| • Initialized Laravel 11 project with required configurations |  |
| • Set up Git repository on GitHub with initial commit and proper. gitignore |  |
| • Created database migrations for core tables: users, venues, packages, services, inquiries |  |
| • Implemented Eloquent model classes with relationships defined |  |
| • Installed and configured required packages: Spatie Permission, DomPDF, Laravel Excel |  |
| Problems Encountered |  |
| Client Availability Challenges - Initial difficulty scheduling meetings with all stakeholders due to hotel's busy event season (December holidays) - Resolution: Conducted multiple shorter sessions and utilized WhatsApp for async clarification |  |
| Complexity of Pricing Rules - The hotel's pricing structure proved more complex than initially anticipated, with multiple seasonal variations, weekend surcharges, and tiered guest pricing - Resolution: Spent additional time documenting all pricing scenarios and designed a flexible dynamic pricing engine architecture Legacy Data Format Issues - Existing data in Excel spreadsheets had inconsistent formatting and duplicate entries - Resolution: Created data cleaning strategy and documented data migration approach for go-live phase |  |
| UI/UX Iteration - Client requested significant changes to initial dashboard wireframes after first review - Resolution: Conducted additional design session and created revised mockups incorporating feedback |  |
| Planned work that were unable to carry out with reasons |  |
| Authentication Module Implementation (Partially Delayed) - While authentication scaffolding was set up, full implementation of role-based access control was moved to next period - Reason: Additional time spent on comprehensive database design and UI revisions - Impact: Minor - Authentication is first task for PR2 and schedule remains on track |  |
| Email Template Setup - Email template management was planned but deferred - Reason: Prioritized core database schema and project foundation - Impact: None - This is scheduled for later phase (PR5) |  |
| Work planned until next meeting |  |
| Authentication & Authorization Module (Week 7-8) - Complete user registration with email verification - Implement secure login with session management - Configure Spatie Permission package for role-based access control - Create five user roles with permission matrix - Implement user profile management and activity logging |  |
| Venue & Calendar Management Module (Week 9-10) - Implement venue CRUD operations with image gallery - Integrate FullCalendar library for interactive availability calendar - Create real-time availability checking with conflict detection - Implement color-coded calendar (Available/Booked/Tentative/Blocked) |  |
| Package & Service Management Module (Week 11-12) - Implement package CRUD with versioning for pricing history - Create service catalog management - Build dynamic pricing engine with guest count tiers and surcharges - Create package comparison tool |  |
| Testing & Documentation - Write unit tests for authentication, availability, and pricing services - Update technical documentation |  |

| Supervisor’s Comments |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Student has done | More than enough; X; Sufficient; Not Enough; No. | work. |
| Student is progressing |  | Well ahead; X; Sufficiently; Not Enough. | in the project. |
| Further Comments (if any) |  |  |  |  |  |
| Student’s Signature |  |  |  | Supervisor’s Signature |  |