IT5106 - Software Development Project

Progress Report - 1

Academic Year - 2025

Project Identification Information

| Project Title | : Wedding and Event Management System for Chance Palace Hotel Group |
| --- | --- |
| Student Name | : W. A. A. D. Wijesingha |
| Index No. | : 2014173 |
| Supervisor | : Ranula Gihara Gamage |

Progress Report Period

| Start Date: 24th November 2025 | End Date: 5th January 2026 |
| --- | --- |

Work Carried Out Between This Meeting and Previous Meeting

1. Requirement Gathering & Analysis (Week 1-2)

- Conducted initial client meeting with Chance Palace Hotel Group management to understand current operational challenges

- Documented existing manual processes including email correspondence, Excel-based booking tracking, and WhatsApp communication workflows

- Interviewed key stakeholders: General Manager, Event Manager, and Sales Staff

- Analyzed existing quotation templates, contract documents, and pricing structures

- Compiled detailed specifications for all five venues: Grand Ballroom, Garden Terrace, Rooftop Pavilion, Conference Hall, and Poolside Area

- Documented package details for Silver, Gold, Platinum, and Custom packages

- Identified integration requirements for email (SMTP) and SMS gateway services

- Created comprehensive Software Requirements Specification (SRS) document

2. Feasibility Study (Week 3)

- Completed technical feasibility assessment confirming Laravel 11, PHP 8.2+, and MySQL 8.0 as appropriate technologies

- Conducted economic feasibility analysis demonstrating projected ROI through reduced administrative overhead

- Assessed operational feasibility including staff training requirements and change management considerations

- Performed risk assessment and documented mitigation strategies

- Compiled complete feasibility study report

3. System Architecture & UI/UX Design (Week 4)

- Designed high-level system architecture following layered architecture pattern

- Created detailed architecture documentation including component diagrams

- Designed UI wireframes for public-facing website (home, venues, packages, inquiry pages)

- Designed UI wireframes for admin dashboard (booking management, calendar, reports)

- Designed UI wireframes for client portal (booking tracking, payment history, documents)

- Created high-fidelity UI mockups using Figma

- Conducted client review session and incorporated feedback

4. Database Design & Project Setup (Week 5-6)

- Designed comprehensive Entity-Relationship Diagram (ERD) covering 25+ entities

- Normalized database schema to Third Normal Form (3NF)

- Created detailed table structures with appropriate constraints, indexes, and foreign key relationships

- Set up local development environment using Laragon with PHP 8.2 and MySQL 8.0

- Initialized Laravel 11 project with required configurations

- Set up Git repository on GitHub with initial commit and proper .gitignore

- Created database migrations for core tables: users, venues, packages, services, inquiries

- Implemented Eloquent model classes with relationships defined

- Installed and configured required packages: Spatie Permission, DomPDF, Laravel Excel

Problems Encountered

1. Client Availability Challenges

- Initial difficulty scheduling meetings with all stakeholders due to hotel's busy event season (December holidays)

- Resolution: Conducted multiple shorter sessions and utilized WhatsApp for async clarification

2. Complexity of Pricing Rules

- The hotel's pricing structure proved more complex than initially anticipated, with multiple seasonal variations, weekend surcharges, and tiered guest pricing

- Resolution: Spent additional time documenting all pricing scenarios and designed a flexible dynamic pricing engine architecture

3. Legacy Data Format Issues

- Existing data in Excel spreadsheets had inconsistent formatting and duplicate entries

- Resolution: Created data cleaning strategy and documented data migration approach for go-live phase

4. UI/UX Iteration

- Client requested significant changes to initial dashboard wireframes after first review

- Resolution: Conducted additional design session and created revised mockups incorporating feedback

Planned Work That Were Unable to Carry Out with Reasons

1. Authentication Module Implementation (Partially Delayed)

- While authentication scaffolding was set up, full implementation of role-based access control was moved to next period

- Reason: Additional time spent on comprehensive database design and UI revisions

- Impact: Minor - Authentication is first task for PR2 and schedule remains on track

2. Email Template Setup

- Email template management was planned but deferred

- Reason: Prioritized core database schema and project foundation

- Impact: None - This is scheduled for later phase (PR5)

Work Planned Until Next Meeting

Period: 6th January 2026 - 16th February 2026 (Progress Report 2)

1. Authentication & Authorization Module (Week 7-8)

- Complete user registration with email verification

- Implement secure login with session management

- Configure Spatie Permission package for role-based access control

- Create five user roles with permission matrix

- Implement user profile management and activity logging

2. Venue & Calendar Management Module (Week 9-10)

- Implement venue CRUD operations with image gallery

- Integrate FullCalendar library for interactive availability calendar

- Create real-time availability checking with conflict detection

- Implement color-coded calendar (Available/Booked/Tentative/Blocked)

3. Package & Service Management Module (Week 11-12)

- Implement package CRUD with versioning for pricing history

- Create service catalog management

- Build dynamic pricing engine with guest count tiers and surcharges

- Create package comparison tool

4. Testing & Documentation

- Write unit tests for authentication, availability, and pricing services

- Update technical documentation

Supervisor's Comments

| Student has done | ☐ More than enough ☐ Sufficient ☐ Not Enough ☐ No work |
| --- | --- |

| Student is progressing | ☐ Well ahead ☐ Sufficiently ☐ Not Enough |
| --- | --- |

| Further Comments |  |
| --- | --- |

| Student's Signature | Supervisor's Signature |
| --- | --- |